## Sprint Board
Account Mining — Sprint Board
AI Value Discovery ¦ Interns: Pragya · Gauravi · Samarth ¦ June 2026
Ticket ID | Title | Assignee | Category | Description | Acceptance Criteria | Status
AM-01 | Chatbot UI — Welcome & Name Entry Screen | Pragya | Frontend | Build the opening screen. User enters their name and department before the conversation starts. | Name & dept fields present. Cannot proceed without filling both. HCL blue/purple theme. | To Do
AM-02 | Chatbot Conversation Flow — 3 Questions | Pragya | Frontend | Build the chat message flow for Q1, Q2, Q3. Each question appears after the previous answer is submitted. | All 3 questions appear in sequence. Answers captured. UI feels like a chat (bubbles, avatars). | To Do
AM-03 | Follow-up Probe UI Logic | Pragya | Frontend | If a user's answer is very short or vague, the chatbot shows a follow-up question before moving on. | Short answers trigger follow-up. Response captured before next question. No broken flow. | To Do
AM-04 | Result Screen — Category Badge & Priority Score | Pragya | Frontend | After all steps, show: idea summary, category badge (Automation / Process Fix / AI Use Case), priority score, animated progress bar, and restart button. | All result fields display correctly. Bar animates. Restart clears and resets the full flow. | To Do
AM-05 | Claude API Integration — Idea Classification | Gauravi | AI / Data | Send the 3 conversation answers to Claude API. Prompt it to return the best idea, its category, and a reason — as structured JSON. | API call works. Returns valid JSON: idea_summary, category, category_reason. Handles API errors gracefully. | To Do
AM-06 | Prompt Engineering — Classification Accuracy | Gauravi | AI / Data | Write and refine the classification prompt. Test with 10+ sample answers. Ensure correct category for clear-cut and edge cases. | 10 test cases pass. Vague answers handled. Prompt version is documented. | To Do
AM-07 | Scoring Formula — A x B x C | Gauravi | AI / Data | Collect A (time in mins), B (frequency/week), C (% reduction). Calculate score = A x B x (C/100). Map to tier: High 300+, Medium 100–299, Low <100. | Formula correct. All 3 inputs validated. Score and tier shown correctly in result screen. | To Do
AM-08 | Input Validation & Data Sanitisation | Gauravi | AI / Data | Validate all inputs before API call or scoring. Name not empty. A, B, C are positive numbers. C is between 1 and 100. | Bad inputs show helpful error messages. API never called with empty or invalid data. | To Do
AM-09 | Idea Storage — Save Submissions to Tracker | Samarth | Backend | After each session, save the idea to a backend store (JSON or lightweight DB). Fields: name, dept, idea summary, category, A, B, C, score, timestamp. | Each submission saved. Data persists across sessions. No duplicate entries for same session. | To Do
AM-10 | API Proxy & Error Handling | Samarth | Backend | Set up a backend proxy to handle Claude API calls securely (no key exposed in frontend). Return clean error responses if API fails. | API key not visible in browser. Errors return structured JSON. Frontend shows friendly message on failure. | To Do
AM-11 | End-to-End Integration Testing | Samarth | Backend | Test the full flow: frontend → backend → Claude API → scoring → result screen. Cover happy path, vague answers, invalid inputs, and API timeouts. | All test scenarios documented. No broken flows. API timeout shows friendly error, not a crash. | To Do
AM-12 | UAT Support & Final Bug Fixes | Samarth | Backend | Support the CoE facilitator during user testing. Log bugs, verify fixes, sign off on final build. | UAT checklist completed. All High priority bugs fixed before handover. | To Do

## Pragya
Pragya — Frontend & UX
Account Mining ¦ AI Value Discovery ¦ June 2026
Ticket ID | Title | Assignee | Category | Description | Acceptance Criteria | Status
AM-01 | Chatbot UI — Welcome & Name Entry Screen | Pragya | Frontend | Build the opening screen. User enters their name and department before the conversation starts. | Name & dept fields present. Cannot proceed without filling both. HCL blue/purple theme. | To Do
AM-02 | Chatbot Conversation Flow — 3 Questions | Pragya | Frontend | Build the chat message flow for Q1, Q2, Q3. Each question appears after the previous answer is submitted. | All 3 questions appear in sequence. Answers captured. UI feels like a chat (bubbles, avatars). | To Do
AM-03 | Follow-up Probe UI Logic | Pragya | Frontend | If a user's answer is very short or vague, the chatbot shows a follow-up question before moving on. | Short answers trigger follow-up. Response captured before next question. No broken flow. | To Do
AM-04 | Result Screen — Category Badge & Priority Score | Pragya | Frontend | After all steps, show: idea summary, category badge (Automation / Process Fix / AI Use Case), priority score, animated progress bar, and restart button. | All result fields display correctly. Bar animates. Restart clears and resets the full flow. | To Do

## Gauravi
Gauravi — AI / Data & Prompting
Account Mining ¦ AI Value Discovery ¦ June 2026
Ticket ID | Title | Assignee | Category | Description | Acceptance Criteria | Status
AM-05 | Claude API Integration — Idea Classification | Gauravi | AI / Data | Send the 3 conversation answers to Claude API. Prompt it to return the best idea, its category, and a reason — as structured JSON. | API call works. Returns valid JSON: idea_summary, category, category_reason. Handles API errors gracefully. | To Do
AM-06 | Prompt Engineering — Classification Accuracy | Gauravi | AI / Data | Write and refine the classification prompt. Test with 10+ sample answers. Ensure correct category for clear-cut and edge cases. | 10 test cases pass. Vague answers handled. Prompt version is documented. | To Do
AM-07 | Scoring Formula — A x B x C | Gauravi | AI / Data | Collect A (time in mins), B (frequency/week), C (% reduction). Calculate score = A x B x (C/100). Map to tier: High 300+, Medium 100–299, Low <100. | Formula correct. All 3 inputs validated. Score and tier shown correctly in result screen. | To Do
AM-08 | Input Validation & Data Sanitisation | Gauravi | AI / Data | Validate all inputs before API call or scoring. Name not empty. A, B, C are positive numbers. C is between 1 and 100. | Bad inputs show helpful error messages. API never called with empty or invalid data. | To Do

## Samarth
Samarth — Backend & Integration
Account Mining ¦ AI Value Discovery ¦ June 2026
Ticket ID | Title | Assignee | Category | Description | Acceptance Criteria | Status
AM-09 | Idea Storage — Save Submissions to Tracker | Samarth | Backend | After each session, save the idea to a backend store (JSON or lightweight DB). Fields: name, dept, idea summary, category, A, B, C, score, timestamp. | Each submission saved. Data persists across sessions. No duplicate entries for same session. | To Do
AM-10 | API Proxy & Error Handling | Samarth | Backend | Set up a backend proxy to handle Claude API calls securely (no key exposed in frontend). Return clean error responses if API fails. | API key not visible in browser. Errors return structured JSON. Frontend shows friendly message on failure. | To Do
AM-11 | End-to-End Integration Testing | Samarth | Backend | Test the full flow: frontend → backend → Claude API → scoring → result screen. Cover happy path, vague answers, invalid inputs, and API timeouts. | All test scenarios documented. No broken flows. API timeout shows friendly error, not a crash. | To Do
AM-12 | UAT Support & Final Bug Fixes | Samarth | Backend | Support the CoE facilitator during user testing. Log bugs, verify fixes, sign off on final build. | UAT checklist completed. All High priority bugs fixed before handover. | To Do

## By Assignee
Work Allocation Summary
Account Mining ¦ AI Value Discovery ¦ June 2026
Assignee | Role Focus | Tickets | Story Points | Key Responsibility
Pragya | Frontend & UX | AM-01, AM-02, AM-03, AM-04 | 14 | Build the full chatbot UI — welcome screen, chat flow, follow-up logic, result display
Gauravi | AI / Data & Prompting | AM-05, AM-06, AM-07, AM-08 | 12 | Claude API integration, prompt engineering for classification, scoring formula, input validation
Samarth | Backend & Integration | AM-09, AM-10, AM-11, AM-12 | 14 | Idea storage, secure API proxy, end-to-end integration testing, UAT support